Proposal: Customer Data Platform Review — Meridian Retail BV

# 1. Executive Summary

Meridian Retail BV has asked us to review its customer data landscape and recommend a path to consolidation.

We will assess the current state, identify the principal risks, and deliver a recommendation the leadership team can act on within the quarter.

# 2. Scope of Work

Our work will cover Meridian's customer-facing data systems. We will review current data flows, interview key stakeholders, and produce findings and recommendations.

The engagement is advisory; implementation is out of scope.

# 3. Approach and Timeline

The engagement runs over eight weeks in three phases: Discovery (weeks 1-3), Analysis (weeks 4-6), and Recommendation (weeks 7-8).

A single steering checkpoint is held at the close of each phase.

# 4. Fees and Payment

A fixed fee of EUR 48,000 covers the engagement in full, invoiced in three instalments at the close of each phase.

The fee assumes the scope set out in section 2 and no more than twelve stakeholder interviews.

# 5. Assumptions and Exclusions

We assume Meridian provides access to systems documentation within one week of kickoff.

Excluded: data migration, tooling procurement, and any hands-on implementation work.